## Advertiser Dashboard Process
Advertiser Dashboard Process
Numbers | Function name | Process | Notes | Status | Last Update
1 | Dashboard overview |  |  | Waitting review | 16-3-2014
| + This page presents an overview of impressions, clicks and CTA map values group by date. + URL to access dashboard overview: http://reporting.vervemobile.com/AdvertiserDashboard/?f=1&p=overview + Api URL used to get data: http://reporting.vervemobile.com/advertiserapi/AdvertiserByDate | Design template | overview.jsp | Done | 16-3-2014
|  | Show chart |  | Done | 16-3-2014
|  | Show table data |  | Done | 16-3-2014
|  | Export report to pds,csv,xls | jasperReports/daily_advertiser_report.jrxml | Done | 16-3-2014
|  | Apply Advertiser filter |  | Pending | 16-3-2014
2 | Daily Advertiser Group By Hour |  |  | Waitting review | 16-3-2014
| + URL to access dashboard overview: http://reporting.vervemobile.com/AdvertiserDashboard/?f=1&p=dailyAdvertisers + Api URL used to get data: http://reporting.vervemobile.com/advertiserapi/AdvertiserByHour | Design template | dailyAdvertisers.jsp | Done | 16-3-2014
|  | Show chart |  | Done | 16-3-2014
|  | Show table data |  | Done | 16-3-2014
|  | Export report to pds,csv,xls | jasperReports/daily_advertiser_report_by_hour.jrxml | Done | 16-3-2014
|  | Apply Advertiser filter |  | Pending | 16-3-2014
3 | Daily Advertiser Group By Distance |  |  | Waitting review | 16-3-2014
| + URL to access dashboard overview: http://reporting.vervemobile.com/AdvertiserDashboard/?f=1&p=dailyAdvertisers + Api URL used to get data: http://reporting.vervemobile.com/advertiserapi/AdvertiserByDistance | Design template | dailyAdvertisers.jsp | Done | 16-3-2014
|  | Show chart |  | Done | 16-3-2014
|  | Show table data |  | Done | 16-3-2014
|  | Export report to pds,csv,xls | jasperReports/daily_advertiser_report_by_distance.jrxml | Done | 16-3-2014
|  | Apply Advertiser filter |  | Pending | 16-3-2014
4 | Daily Advertiser Group By DMA |  |  | Waitting review | 16-3-2014
| + URL to access dashboard overview: http://reporting.vervemobile.com/AdvertiserDashboard/?f=1&p=dailyAdvertisers + Api URL used to get data: http://reporting.vervemobile.com/advertiserapi/AdvertiserByDma | Design template | dailyAdvertisers.jsp | Done | 16-3-2014
|  | Add DMA filter |  | Done | 16-3-2014
|  | Show chart |  | Done | 16-3-2014
|  | Show table data |  | Done | 16-3-2014
|  | Export report to pds,csv,xls | jasperReports/daily_advertiser_report_by_dma.jrxml | Done | 16-3-2014
|  | Apply Advertiser filter |  | Pending | 16-3-2014
5 | Campaign Name |  |  | Processing | 16-3-2014
|  | Design template | campaign.jsp | Done | 16-3-2014
|  | Dimesions Filter |  | Pending | 16-3-2014
|  | Show chart |  | Pending | 16-3-2014
|  | Show table data |  | Pending | 16-3-2014
|  | Export report to pds,csv,xls |  | Pending | 16-3-2014

## Advertiser API
Advertiser API
Numbers | API name | Table source | Access URL | Notes | Last Update
API Overview
1 | Advertiser by Date | binh.agg_creatives_by_date | http://reporting.vervemobile.com/advertiserapi/AdvertiserByDate |  | 2014-03-16
2 | Advertiser by Hour | binh.agg_creatives_by_hour | http://reporting.vervemobile.com/advertiserapi/AdvertiserByHour |  | 2014-03-16
3 | Advertiser by Distance | binh.agg_creatives_by_distance | http://reporting.vervemobile.com/advertiserapi/AdvertiserByDistance |  | 2014-03-16
4 | Advertiser by DMA | binh.agg_creatives_by_dma | http://reporting.vervemobile.com/advertiserapi/AdvertiserByDma |  | 2014-03-16
Dimension Lookup
1 | Orders | binh.dim_orders | http://reporting.vervemobile.com/advertiserapi/LookupOrders |  | 2014-03-16
2 | Flights | binh.dim_flights | http://reporting.vervemobile.com/advertiserapi/LookupFlights |  | 2014-03-16
3 | Creatives | binh.dim_creatives | http://reporting.vervemobile.com/advertiserapi/LookupCreatives |  | 2014-03-16

## Software & Libraries
Software & Libraries for development
Numbers | Name | Description
1 | Tomcat server | Use to deploy web application Version: 6 Donwload: https://tomcat.apache.org/download-60.cgi
2 | Eclipse EE | Use this tool to develop web site Download: https://www.eclipse.org/downloads/packages/eclipse-ide-java-ee-developers/keplersr2
3 | iReport Designer | Use this tool to design export template Version: 3.7.6 Download: http://sourceforge.net/projects/ireport/files/iReport/iReport-3.7.6/
4 | JasperReports Library | Requirement library to export report to csv,pdf,xls Download: http://sourceforge.net/projects/ireport/files/iReport/iReport-3.7.6/
5 | Bootrap 3 - front-end framework | This library used to design web template for web interface Version: 3.0 Download: http://getbootstrap.com/getting-started/#download
6 | Bootstrap DateRangePicker | Date range picker component for Bootstrap Version: 1.0 Download: https://github.com/dangrossman/bootstrap-daterangepicker
7 | HightChart | Use this library to draw chart on web interface Version: 3.0.4 Download: http://www.highcharts.com/download
8 | JQuery | Requirement library used to code java script Version: 2.0 Download: http://code.jquery.com/jquery-2.1.0.min.js
9 | Select2 | This library used to design web template for web interface in filter dimensions Version: 3.4.3 Download: https://github.com/ivaynberg/select2/archive/3.4.3.zip

## Deployment log
Deployment Log
Server environment:
Dw0
Installed tomcat server 6. Location at : /opt/pentaho/biserver-ce/tomcat/
Java library 1.6
Location:
/opt/pentaho/biserver-ce/tomcat/webapps/advertiserapi
/opt/pentaho/biserver-ce/tomcat/webapps/AdvertiserDashboard
Advertiser deployment log
Date | Updates
2014-03-16 | Deploy the first time
Advertiser Api deployment log
Date | Updates
2014-03-16 | Deploy the first time